## Program
McHenry County Council of Mayors STP Schedule (FFY 2026 - FFY 2030)
FFY 2026 - October 1, 2025 thru September 30, 2026
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting/ Auth Date | Project Type
11-22-0031 | Boyer Road | Algonquin | CON/CE | 1018000 | 1450039 | 2468039 | No Current Requests | decreased by $49,961 due to smaller funding mark (10/24) | 9/30/2026 | 4/2026 | Roadway & Intersection
11-22-0027 | Ballard Road | Lakewood | CON/CE | 267468 | 1023946 | 1291414 | No Current Requests | decreased by $45,927 due to smaller funding mark (3/2024) | 9/30/2026 | Q1, 2026 | Resurfacing
11-22-0028 | Queen Ann Road | Bull Valley | CON/CE | 178542 | 714170 | 892712 | No Current Requests |  | 9/30/2026 | Q1, 2026 | Resurfacing
11-21-0010 | Kreutzer Road | Huntley | CON/CE | 958745 | 1400967 | 2359712 | No Current Requests | Planned use of $6,773,925 from redistribution (3/2025) ITEP grant of $3,000,000 | 9/30/2030 | 4/2026 | Roadway & Intersection
11-24-0016 | Diggins-Sumner | Harvard | E1 | 21990 | 87960 | 109950 | No Current Requests | Moved from FY25 PUD funds for fiscal constraint | 9/30/2028 | TBD | Resurfacing
11-22-0038 | Winn Road/East Solon Road | Spring Grove | CON/CE | 151984 | 607936 | 759920 | No Current Requests | Cost increase request to $798,967, limited to 20% of $607,936 bc Redistribution. Cost increase trying to get to 80/20 split | 9/30/2026 | Q1, 2026 | Resurfacing
Planned Use of Redistribution
11-21-0010 | Kreutzer Road | Huntley | CON/CE | 1448826 | 8229316 | 9678142 | No Current Requests | Planned use of $8,130,283 from redistribution (11/2025) ITEP grant of $3,000,000 | 9/30/2030 | 4/2026 | Roadway & Intersection
11-24-0019 | Commercial Street | Richmond | E1 | 14500 | 58000 | 72500 | No Current Requests | Extension to March 30 | 9/30/2025 | 1/2029 | Resurfacing
11-22-0026 | Marengo Road | Harvard | CON/CE | 150000 | 1350000 | 1500000 | No Current Requests | Cost Increase due to misunderstanding on Toll Credits (initial request would have been higher) | 9/30/2026 | 9/2026 | Resurfacing
11-24-0021 | Crystal Lake Road | Lake in the Hills | CON/CE | 189640 | 758560 | 948200 | No Current Requests |  | 9/30/2028 | 11/2026 | Resurfacing
CONTINGENCY | Harmony Road Bridge | McHenry County | CON/CE | 300000 | 0 |  | 1500000 |  |  |  | Roadway & Intersection
TOTALS |  |  |  |  | 5285018
FFY26 Allotment: | 5285018 | Carryover from FY25: | 0 | FFY26 Mark: | 5285018 | Left Over $: | 0 | FY26 Planned Use of Redistrbution: | 10395876
FFY 2027 - October 1, 2026 thru September 30, 2027
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting/ Auth Date | Project Type
11-22-0033 | Ringwood Road/Fox Lake Road | Johnsburg | CON/CE | 860245 | 1500000 | 2360245 | No Current Requests |  | 9/30/2027 | Q1, 2027 | Resurfacing
11-26-0005 | Square Barn Rd | Algonquin | CON/CE | 226793 | 907172 | 1133965 |  | Moved from Contingency 3/2026 |  | Q2, 2027
11-22-0035 | Frank Road | Lake in the Hills | CON/CE | 667000 | 1500000 | 2167000 | No Current Requests |  | 9/30/2027 | Q1, 2027 | Roadway & Intersection
11-22-0036 | Barreville Road | Prairie Grove, McHenry | CON/CE | 350870 | 1403478 | 1754348 | No Current Requests | $9442 returned | 9/30/2027 | Q1, 2027 | Resurfacing
TOTALS |  |  |  |  | 5310650
FFY27 Allotment: | 5310650 | Carryover from FY26: | 0 | FFY27 Mark: | 5310650 | Left Over $: | 0
FFY 2028 - October 1, 2027 thru September 30, 2028
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting/ Auth Date | Project Type
11-20-0015 | Howe/Wonder Lake Road | Greenwood | CON/CE | 37511 | 337600 | 375111 | No Current Requests | Moved $108,000 to PUR (7/25). Original proposal from 2020, increase due to rising construction costs | 9/30/2030 | Q1 2030 | Roadway & Intersection
11-24-0015 | North Main Street | Algonquin | CON/CE | 375000 | 1500000 | 1875000 | No Current Requests |  | 9/30/2028 | 11/2027 | Roadway & Intersection
11-24-0016 | Diggins-Sumner | Harvard | E2 | 25950 | 103800 | 129750 | No Current Requests |  | 9/30/2028 | TBD | Resurfacing
11-24-0017 | Main Street-Liberty Road | Crystal Lake | CON/CE | 375000 | 1500000 | 1875000 | No Current Requests |  | 9/30/2028 | TBD | Roadway & Intersection
11-24-0018 | Thompson Road | Bull Valley | E2 | 5156.25 | 20625 | 25781.25 | No Current Requests |  | 9/30/2028 | TBD | Resurfacing
11-24-0018 | Thompson Road | Bull Valley | CON/CE | 122100 | 488400 | 610500 | No Current Requests | Moved from FY29 due to fiscal constraint | 9/30/2029 | TBD | Resurfacing
11-24-0019 | Commercial Street | Richmond | E2 | 12750 | 51000 | 63750 | No Current Requests |  | 9/30/2028 | TBD | Resurfacing
11-24-0020 | Oak/Industrial/Orleans | McHenry | E1 | 10000 | 40000 | 50000 | No Current Requests |  | 9/30/2025 | TBD | Resurfacing
11-24-0020 | Oak/Industrial/Orelans | McHenry | E2 | 10000 | 40000 | 50000 | No Current Requests |  | 9/30/2028 | TBD | Resurfacing
11-21-0007 | Green Street Milling and Resurfacing | McHenry | CON/CE | 6250 | 25000 | 31250 | No Current Requests | Project completed, waiting on final invoice | 9/30/2028 | TBD | Resurfacing
11-21-0006 | Riverside Drive | Johnsburg | CON/CE | 194974 | 779897 | 974871 | No Current Requests | Cost Increase, Project completed, waiting on final invoice | 2023-09-22 | 9/22/2023 | Resurfacing
CONTINGENCY | Charles Road Bridge | McHenry County | CON/CE | 300000 | 0 |  | 1500000 |  |  |  | Roadway & Intersection
CONTINGENCY | Marengo Road Bridge | McHenry County | CON/CE | 300000 | 0 |  | 1500000 |  |  |  | Roadway & Intersection
TOTALS |  |  |  |  | 4886322
FFY28 Allotment: | 5395621 | Carryover from FY27: | 0 | FFY28 Mark: | 5395621 | Left Over $: | 509299
FFY 2029 - October 1, 2028 thru September 30, 2029
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting/ Auth Date | Project Type
11-21-0011 | Johnsburg Road | Johnsburg | CON/CE | 375000 | 154401 | 529401 | No Current Requests | Planned use of $154,401 from Redistribution (3/2025) Moved to FY29 for fiscal constraint | 9/30/2025 | Let 6/2025* | Resurfacing
11-24-0016 | Diggins-Sumner | Harvard | CON/CE | 376931.25 | 1507725 | 1884656.25 | No Current Requests |  | 9/30/2029 | TBD | Resurfacing
11-24-0019 | Commercial Street | Richmond | CON/CE | 319000 | 1276000 | 1595000 | No Current Requests |  | 9/30/2029 | TBD | Resurfacing
11-24-0023 | Running Brook Farm Boulevard | Johnsburg | CON/CE | 286462 | 1145848 | 1432310 | No Current Requests |  | 9/30/2029 | TBD | Resurfacing
11-24-0020 | Oak/Industrial/Orleans | McHenry | CON/CE | 280000 | 1120000 | 1400000 | No Current Requests |  | 9/30/2029 | TBD | Resurfacing
CONTINGENCY | Miller Road | Lake in the Hills | CON/CE | 220000 | 0 |  | 880000 |  |  |  | Resurfacing
TOTALS |  |  |  |  | 5203974
FFY29 Allotment: | 5481951 | Carryover from FY28: | 0 | FFY29 Mark: | 5481951 | Left Over $: | 277977
FFY 2030 - October 1, 2029 thru September 30, 2030
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting/ Auth Date | Project Type
11-26-0014 | Sandbloom Rd | Algonquin | Con/CE | 360000 | 1800000 | 2160000 |  | CON/CE in 30
11-26-0010 | Lakewood & Miller | MCDOT | Con/CE | 360000 | 1800000 | 2160000 |  | No year included
11-24-0014 | High Rd Extension | Cary | Con/CE | 360000 | 1800000 | 2160000 |  | Con/CE in 29
11-26-0011 | English Prairie Rd | Spring Grove | Phase II | 5000 | 25000 | 30000 |  | requested Phase 2 in 27
11-26-0013 | Barnard Mill Rd | Ringwood | Phase II | 6500 | 32500 | 39000 |  | requested Phase 2 in 27
CONTINGENCY | South St | Woodstock | Con/CE |  |  |  |  | Requested $1,800,000
CONTINGENCY | Calhoun St | Woodstock | Con/CE |  |  |  |  | Requested $1,486,323
CONTINGENCY | Miller Rd | LITH | Con/CE |  |  |  |  | Requested $1,282,176
CONTINGENCY | Ames Rd | Prairie Grove | Con/CE |  |  |  |  | Requested $812,300
CONTINGENCY | Huntley Rd | Lakewood | Con/CE |  |  |  |  | Requested $513,100
CONTINGENCY | Oak St. | LITH | Con/CE |  |  |  |  | Requested $1,032,192
TOTALS |  |  |  |  | 5457500
FFY30 Allotment: | 5481951 | Carryover from FY28: | 0 | FFY30 Mark (est): | 5481951 | Left Over $: | 24451
FFY 2031 - October 1, 2030 thru September 30, 2031
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting/ Auth Date | Project Type
11-26-0011 | English Prairie Rd | Spring Grove | Con/CE | 217014.4 | 1085072 | 1302086.4 |  | CON in 28
11-26-0013 | Barnard Mill | Ringwood | Con/CE | 349599.2 | 1747996 | 2097595.2 |  | CON in 28
11-26-0012 | East Wonder Lake Rd | Wonder Lake | Con/CE | 360000 | 1800000 | 2160000 |  | CON in 30
11-26-0016 | Marengo Rd | Harvard | Phase 1 | 40000 | 200000 | 240000 |  | No year included
11-26-0015 | Algonquin Rd & Lincoln Ave | Fox River Grove | Con/CE | 129776.6 | 648883 | 778659.6 |  | CON in 30
CONTINGENCY | Golf Course Rd | Crystal Lake | Con/CE |  |  |  |  | Requested $1,767,790
CONTINGENCY | McCullom Lake Rd | Johnsburg | PH2/CON/CE |  |  |  |  | Requested $1,477,376
TOTALS |  |  |  |  | 5481951
FFY30 Allotment: | 5481951 | Carryover from FY28: | 0 | FFY31 Mark (est): | 5481951 | Left Over $: | 0
[10 empty] | Last Revised: | 2026-07-21
[10 empty] | Last Approved: | 2026-09-22

## Sheet1
TIP # | Project Name | Agency | Project Phase | Match Amount | Programmed STP | Phase Total | STP Funding Increase Request | Notes | Authorization Deadline | Target Letting | Project Type
11-20-0015 | Howe Road | Greenwood | CON/CE | 24037 | 0 | 24037 | No Current Requests | Planned use of $216,329 from Redistribution (12/24) | 9/30/2024 | 6/2025* | Roadway & Intersection
11-21-0003 | Prospect Street | Marengo | CON/CE | 760000 | 1500000 | 2260000 | No Current Requests | Planned use of $1,200,000 in redistribution (11/24) | 3/31/2025 | 6/2025 | Resurfacing
11-21-0006 | Riverside Drive | Johnsburg | CON/CE | 194974.25 | 779897 | 779897 | No Current Requests | Per approved request, supplemental cost increase (10/2024) | 9/30/2025 | Let 9/2023 | Resurfacing
11-21-0010 | Kreutzer Road | Huntley | CON/CE | 4770000 | 1500000 | 6270000 | No Current Requests | Planned use of $5,273,925 from redistribution | 9/30/2025 | 6/2025 | Roadway & Intersection
11-21-0011 | Johnsburg Road | Johnsburg | CON/CE | 375000 | 1165968 | 1540968 | No Current Requests | Planned use of $534,032 from Redistribution (10/2024) | 9/30/2025 | 6/2025* | Resurfacing
11-22-0003 | Three Oaks/Lutter/Sands | Crystal Lake | CON/CE | 163669.405 | 0 | 2154677.62 | No Current Requests | Supplemental Cost Increase of $654,678 to be granted once 75% of obligated funds expended | 9/30/2025 | Let 4/2024 | Resurfacing
11-22-0026 | Marengo Road | Harvard | E2 | 72000 | 108000 | 180000 | No Current Requests | Increased by $18,000 to reflect use of Toll Credits (10/2024) | 9/30/2025 | 11/2025 | Resurfacing
11-22-0029 | First Street | Cary | CON/CE | 263500 | 1054000 | 1317500 | No Current Requests |  | 9/30/2025 | Let 1/2025 | Resurfacing
11-22-0034 | West Wonder Lake Road | Wonder Lake | CON/CE | 180583 | 722328 | 902911 | No Current Requests |  | 9/30/2025 | Let 1/2025 | Resurfacing
11-22-0036 | Barreville Road | Prairie Grove, McHenry | E1 | 32000 | 12000 | 44000 | No Current Requests |  | 9/30/2025 | Q1, 2025 | Resurfacing
11-22-0036 | Barreville Road | Prairie Grove, McHenry | E2 | 50000 | 30000 | 80000 | No Current Requests |  | 9/30/2025 | Q1, 2025 | Resurfacing
11-22-0037 | Raffel Road | Woodstock | CON/CE | 325922.5 | 0 | 325923 | No Current Requests | Planned use of $1,303,690 from Redistribution (12/24) | 9/30/2025 | 11/2025 | Resurfacing
11-24-0016 | Diggins-Sumner | Harvard | E1 | 21990 | 87960 | 109950 | No Current Requests |  | 9/30/2025 | TBD | Resurfacing
11-24-0019 | Commercial Street | Richmond | E1 | 14500 | 58000 | 72500 | No Current Requests |  | 9/30/2025 | 1/2029 | Resurfacing
11-24-0022 | Nish Road | Prairie Grove | CON/CE | 0 | 0 | 0 | No Current Requests | Planned use of $755,840 from redistribution | 9/30/2025 | 6/2025 | Resurfacing